## Sheet1
Client Details
| Client Name | Anti Theft Mobile Tracker
| Profession | Anti Theft Mobile Tracker
| Date | 13th Sep 2019
| Referance Application | https://play.google.com/store/apps/details?id=com.wardwiz.androidsecurity&hl=en
https://play.google.com/store/apps/details?id=com.atmthub.antitheftapp&hl=en
Sr No. | Module Covered (Application) | Working Hours | Sr No. | Module Covered (Admin panel) | Working Hours
1 | Login (MUST) | 10 | 1 | Login / logout | 4
2 | Signup (MUST) | 10 | 2 | Signup /update | 10
3 | Mobile Verification (MUST) | 10 | 3 | Mobile Verification | 8
4 | SOS | 10 | 4 | SOS | 10
5 | Theft setting (MUST) | 20 | 5 | Theft setting | 10
6 | video OR Audio, photo, location send on sms receive (Notification | 36 | 6 | video, photo, location send on sms receive | 45
7 | Mobile Ring on slient mode (Enable and disable both through SMS) | 24 | 7 | Mobile Ring on slient mode | 8
8 | Charging Disonnect Alaram (If I remove phone from charging, alaram goes ON) | 24 | 8 | Charging Disonnect | 8
9 | Contact send vcf to pdf | 16 | 9 | Contact send vcf to pdf | 16
10 | Reference Facility | 10 | 10 | Reference Facility | 10
11 | Payment Integration | 24 | 11 | Chrone job | 8
12 | Designs / UI | 115 | 12 | admin : login, signup , user detail view , payment , package , timeline , verify reject , payment gateway , settings | 80
|  |  | 13 | user web : login , signup , logs, image view , video view , send sms , action button | 80
|  |  | 14 | Design And UI | 160
| Total Time line in hr base | 309 |  | Total Time in Hours | 457
Total Cost :- 3,25000 (Includes :- Web Site for the web presence of the product, 1 year hosting, 30000 SMSs, 4 Months post immplementation support)
All the user data should be visible in Mobile app
Can't disable SMS notifications
Study WardWiz App.
| Format mobile throught SMS command | Not feasible technically (data can be deleted but format can't be done)
| SIM Card Lock (only particular SIM card will work and no other SIM card will work in that phone) | Not feasible tehnically
| Theft phone cannot be restarted or factory restored | Not feasible